## Sheet1
Task | Start | Finish | Completion %
Proposal and Topic Selection | 2024-09-25 | 2024-09-25 | 100
Write Email Proposal | 2024-09-25 | 2024-09-25 | 100
Initial Research and Team Introduction | 2024-09-25 | 2024-12-11 | 75
Team Introduction and Role Assignment | 2024-09-25 | 2024-09-25 | 100
Stakeholder and Ethical Process Research | 2024-09-25 | 2024-12-11 | 50
Structuring the Presentation | 2024-09-25 | 2024-12-11 | 0
Develop Introduction | 2024-09-25 | 2024-12-11 | 0
Research Alternatives and Effects | 2024-09-25 | 2024-12-11 | 0
Consequences and Analysis | 2024-09-25 | 2024-12-11 | 0
Weigh Consequences | 2024-09-25 | 2024-12-11 | 0
Intent and Character Evaluation | 2024-09-25 | 2024-12-11 | 0
Correlate Perspectives | 2024-09-25 | 2024-12-11 | 0
Final Decisions and Summary | 2024-09-25 | 2024-12-11 | 0
Presentation Draft and Review | 2024-09-25 | 2024-12-11 | 0
Create Presentation Slides | 2024-09-25 | 2024-12-11 | 0
Team Practice | 2024-09-25 | 2024-12-11 | 0
Final Review and Presentation | 2024-09-25 | 2024-12-11 | 0
Review and Revise Slides (If needed) | 2024-09-25 | 2024-12-11 | 0
Final Presentation Practice | 2024-09-25 | 2024-12-11 | 0
Presentation | 2024-12-11 | 2024-12-11 | 0